## Project Tracker
STATUS |  |  |  | PROJECT CREATION | [8 empty] | PROJECT DEVELOPMENT | [7 empty] | PROJECT EXECUTION
PRIORITY | PHASE | RECENT STATUS UPDATE | SUB REGION | FACILITY | PROJECT NAME | WO # | CREATION DATE | INITIAL WORK DATE | EXPECTION COMPLETION DATE | PROJECT SUMMARY | LINK TO DECK | CONTRACTOR | QUOTE 1 | QUOTE 2 | QUOTE 3 | EXPENSE REQUEST TYPE | USEFUL LIFE ESTIMATE | FER SUBMISSION | FER # | EST. COST | PRJ CODE | APPROVED COST | EST START | ACTUAL START | EST COMPLETION | ACTUAL COMPLETION | ACTUAL COST | COMPLETION STATUS | COMPLETION PHOTOS
P0 | Project Development | 04/01 - Ricardo is detailing SOW - ETA 04/04 We need to find two roofing vendors 01/09 - Reach out to Kaitlyn to understand if she was able to get a new quote 01/28 - Channel created for the roof coating, Chris will help us build a quote using in-house techs 02/06 - Detail parts of the job, and get quotes for each part | NW | CA_Hayward_1025 A St | Roof Coating | Pending | 2024-11-07 | 2024-12-07 | 2025-04-30 | We need to cover the leaks at the roof. This were mapped out with the construction team. Now we need to get different proposals |  | N/A | 54075 | 18000 | Analyzing FTM | Facility Improvement | 20
P0 | Project Execution | 04/01 - In-house, Darin+1, parts on site; ETA 04/04; Proposal sent- ready for approval 03/20 - Pending approval 03/25 - Vendor Proposal not approved, services scheduled in-house | NW | CA_Sacramento_1501 N C St | Sacramento new exterior lights | 298427608 | 2025-01-30 | 2025-03-01 | 2025-04-04 | WOs in the past: 268647400, 294125444. We have reinstalled the current lights multiple times. We would like to replace it for another model. |  | N/A | 1230 | NA | NA | Repair | 5 | NA | NA | 1800 | NA | NA | 03/27 |  | 03/27
P0 | Project Execution | 04/01- Wiring is ok, most of the project is completed; ETA 04/04 03/24 - Buying parts | NW | CA_San Francisco_1200 Market St | Market Street security improvement | 303478381 | 2025-02-15 | 2025-03-17 | 2025-04-04 | Install new cables to upgrade openpath comms |  | N/A | 3133 | N/A | N/A | Facility Improvement | 5 years | 2025-03-20 | 558 | 3133 | PRJ.0570.07 | 3133 | 03/26 |  | 03/28 |  | 3933
P0 | Project Execution | 4/1 - Scheduled for April 28th to April 30th | SW | CA_Long Beach_1388 Daisy Ave | MAU drains | N/A | - | 2025-04-28 | 2025-04-01 | Water draining from the MAUs go directly to the street | N/A | FTM | N/A | N/A | N/A | Repair | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-20 |  | N/A
P0 | Project Creation | 4/1: eng recommends to Apply sealing paint as a fix | SW | CA_San Diego_2707 Boston Ave | MAU-05 | 285292405 | - | 2024-08-04 | TBD - April 2025 | MAU-05 is currently leaking, drain pan needs to be replaced. Unit has to be dis-assembled to change the pan | Check WO | FTM
P0 | Project Development | 4/1 - Parts on order (ETA 4/4), to be scheduled with Joel and Cesar for April 21st | SW | CA_Anaheim_1560 S Lewis St | MAU-02 blower wheel | N/A | - | 2024-09-01 | 2025-04-23 | MAU 2A: The blower wheel assembly has damaged bearings and a grooved shaft, requiring a full replacement. MAU 2D (Blower #4): The blower wheel assembly also has damaged bearings and a grooved shaft, necessitating a replacement | N/A | FTM / Eng | 7880.46 | N/A | N/A | Facility Improvement | 5 years | 2024-08-21 | 352 | 7880.46 | PRJ.0239.07 | 7880.46 | 2025-04-23 |  | 2025-04-25
P0 | Project Development | 4/1 - The temporary solution will last around 6 months, all the recommendations proposed by the vendor to be completed under project. Expected start date 4/3 | SW | AZ_Tempe_1900 E 5th St | Roof | 305138797 | - | 2025-03-07 | 2025-04-03 | Remove existing roof compromised by moisture and remove drip edge, Install new foam roofing and new drip edge metal. | Link | TBD | 8975 | 8700 | N/A | Facility Improvement | N/A | 2025-03-18 | 557 | 8975 | PRJ.0027.10 | 8975 | 2025-04-03 |  | 2025-04-09 |  | 8975
P0 | Project Development | 4/1 - Vendor's recommendations approved on 3/30. Expected start date 4/10 | SW | AZ_Phoenix_720 W Highland Ave | Roof | 306516223 | - | 2025-03-06 | 2025-04-15 | Remove damaged foam roofing and replace with SPF | Link | TBD | 2500 | 20000 | N/A | Facility Improvement | N/A | 2025-03-28 | 565 | 2500 |  | 2500 | 2025-04-16 |  | 2025-04-18 |  | 2500
P0 | Project Creation | 4/1 - Expense request sent | SW | AZ_Tempe_1900 E 5th St | Grease traps column | 305139552 | - | 2025-02-21 | 2025-04-28 | Replace the concrete columns of both grease traps | N/A | 3D Pipelines | 6307.89 | 6450 | N/A | Facility Improvement
P0 | Project Creation | 4/1 - First camera inspection didn't show any blockage. Second camera inspection scheduled for 4/2 with longer reach | SW | AZ_Tempe_1900 E 5th St | Parking lot drain | 307270329 | - | 2025-03-13 | 2025-04-15 | Drain inspection, camera re-inspection scheduled for 4/1 | N/A | TBD
P0 | Project Creation | 4/1 - Waiting for quote from vendors, Joseph Kemp to send new Openpath Box | SW | AZ_Tempe_1900 E 5th St | Openpath install single door | N/A | - | 2025-03-26 | 2025-04-23 | Joseph Kemp to send additional Openpath box, vendors contacted to provide quote for install | N/A | Downtown Locksmiths
P1 | Project Execution | 04/01 - Team is replacing FRP panels; missing another execution round. ETA 04/08 12/03 - Allign with Darin, get parts and include in scheduling. 01/30 - Count how many FRP boards are needed 02/06 - Buy parts and schedule 03/20 - Schedule full team and add corrections of the lobby. Get lobby pictures and share in the channel to close the channel. | NW | CA_San Francisco_475 6th St | Soma-Hallways Refresh | 302652851 | 2024-12-02 | 2025-01-01 | 2025-04-08 | Clean FRP Better attach the FRP boards to the walls Install bumper guards Repatch the wholes of the shelves that were removed (and replace some panels) |  | N/A | 1200 | N/A | N/A | Facility Improvement | 3 years | NA | NA | 1200 | NA | NA | 02/17 |  | 02/30 |  | NA
P1 | Project Execution | 04/01 - Jay will tackle this when he is back, probably a whole week. ETA 04/15 Cove Base application in progress We need to buy the bumpers 01/09 - Get measurements for the bumpers to bauy and install them 01/23 - Buy cove base and bumper guards 02/06 - Cove base arrived - execution scheduled over the next few days. Buy the bumper guards 03/20 - Schedule north techs 2 days next week | NW | CA_Oakland_5333 Adeline St | Adeline-Hallways Refresh | 302650180 302652158 | 2024-10-01 | 2024-10-31 | 2025-04-15 | Hallways Refresh |  | N/A | FTM | NA | NA | Facility Improvement | 3 | NA | NA | 3000
P1 | Project Creation | 04/01 - Update channel with expected days/scope/details 02/06 - Paint the lobby for the project execution - coordinate with Reza for the execution 03/20 - In theory this is only painting | NW | CA_San Jose_949 Ruff Dr | Ruff Drive Lobby Refresh | Pending | 2025-02-06 | 2025-03-08 |  | Paint the wall and improve the trimm of the lockers
P1 | Project Creation | 04/01 - Deatil scope with Casey | NW | OR_Portland_1135 SE Grand Ave | Portland Trash room heating |  | 03/27
P1 | Project Creation |  | NW | CA_San Francisco_90 Charter Oak Ave | New side door for Charter Oak
P1 | Project Development | 4/1 - Cesar scheduled for 4/24 | SW | CA_Culver City_5668 Selmaraine Dr | Retrofit all MAUs | N/A | - | 2024-09-25 | 2025-04-01 | Retrofit all MAUs with new pumps and float valves | Check WO | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A
P1 | Project Creation | Need to run plumbing line from main line to the water softener (to be completed by FTM), after this, final install to be completed by Culligan | SW | CA_San Diego_6334 El Cajon Blvd | Water heater audit | N/A | - | 2024-03-26 | TBD / June 2025 | Water softener is not working | Link | FTM / Culligan | N/A | N/A | N/A | Facility Improvement
P1 | Project Creation | 4/1 - Project to be completed by construction | SW | CA_Santa Ana_2509 S Broadway | Water softener installation | N/A | - | TBD | TBD | Need to install water softener. Construction working on this | N/A | N/A | N/A | N/A | N/A | N/A
P1 | Project Creation | 4/1 - Selected proposal sent for pre-approval | SW | AZ_Tempe_1900 E 5th St | Exterior lights | 305882961 | - | 2025-02-27 | 2025-04-23 | Install new lights in the parking lot | N/A | JFK Electric | 6500 | 4189 | N/A | Facility Improvement
P1 |  |  | SW | AZ_Tempe_1900 E 5th St | Double door delivery | N/A | - |  |  | Chris will go and evaluate with Jareth
P1 | Project Creation | 4/1 -Parts requested with procurement. Installation in-house | SW | CA_Lawndale_16711 Hawthorne Blvd | Water heater re-circ pump | N/A | - | 2025-03-24 | TBD | Need to replace the water heater recirculation pump | N/A | FTM
P1 | Project Creation | 4/1 - Waiting on quote | SW | CA_Lawndale_16711 Hawthorne Blvd | Fire alarm panel | N/A | - | 2025-03-17 | 2025-04-20 | Need to replace panel due to water damage | N/A | Pacific Signaling
P2 | Project Execution | 04/01 - Revise SOW to validate if we can create a Capex Project for it; 11/19 - Get quotes 12/10 - Captain plumbing 01/09 - Invite Captain Plumbing to meeting 01/14- made contact with Tony Moya (captain plumbing), setting meeting for next week 01/23 - Ricardo to get other quotes 02/06 - 3 quotes completed, ask for approval 03/20 - Pending voided check | NW | UT_Salt Lake City_23 N 900 W | SLC BFP rebuild | Pending | 2024-07-10 | 2024-08-09 | 2024-12-12 | Rebuild the backflow prevention device |  | N/A | 5000 | 1960 | 2388 | Facility Improvement | 10 years | NA | NA | 1960 | NA | NA | 2025-01-04 |  | 2025-10-04 |  | 1960
P2 | Project Development | 04/01 - Pending quote Darin will provide us a proposal 11/19 - Darin declined 12/03 - Dispatched to Bayardo. Scheduled for 12/05 01/09 - Reach out to Bayardo for FUP 02/06- Look for new vendors | NW | CA_San Francisco_90 Charter Oak Ave | Charter Gas Missing Dirt Leg | 302592544 | 2024-09-08 | 2024-10-08 | 12/20 | DEFICIENCY: WATER HEATERS MISSING DIRT LEG AT GAS CONNECTION. MITIGATION: INSTALL DIRT LEG AS REQUIRED PER CODE. |  | N/A | 4032.12 | 4275 | Pending | Facility Improvement
P2 | Project Development | 04/04 - Pending quote from new vendor; 01/28 - Reach out for new quotes: Taylor electric, Fix & Finish 02/05- Taylos electric charges $95 just for the visit 02/06 - Fix&finish doesnt provide this service, only basic electrical jobs 02/06 - Contacted Restaurant Service Solutions /Victor Mendoza, to get an estimate, request sent 03/20 - Still trying to get a new quote for the labor | NW | UT_Salt Lake City_23 N 900 W | SLC Security Breakers | 297573193 | 2024-12-03 | 2025-01-02 | 02/28 | Install the surge protection devices in the main panel |  | Link | 5191.16 | SURGE ARRESTOR DATA SHEET | Taylor electric, trying to get an estimate without visit cost
P2 | Project Creation | 04/01 - Buy parts on 04/08 - and execute as soon as we complete Adeline; 03/20 - Pending bumper guards | NW | CA_San Francisco_90 Charter Oak Ave | Charter Oak Bumper Guards | Pending | 2025-06-02 | 2025-07-02 |  | REAL MEASUREMENT IS 210ft |  |  | FTM
P2 | Project Creation | 04/01 - Quote awning with in-house install or get a broader SOW for Capex; 03/20 - Define project scope | NW | CA_San Jose_949 Ruff Dr | Ruff drive rain protection for catering |  | 2025-03-19 | 2025-04-18 |  |  |  |  | 2306 | 2311
P2 | Project Creation | 04/01 - Get quote from Darin 03/20 - Buy parts | NW | CA_San Mateo_66 21st Ave | San Mateo WH Improvents 2nd phase |  | 2025-03-20 | 2025-04-19 |  | The existing thermal expansion tank is undersized and needs to be replaced with a new Zurn WXTP-50V floor mounted model. Each of the (2) water heater condensate drain lines are missing acid neutralization kits. Provide new Acid Neutralization Kits; Mfr: Neutra-Safe or equal, with inlet and outlet sizes to match existing condensate drain pipe.
P2 | Project Creation | 04/01 - Get detailed SOW with OPS and quote parts+instal 03/27 Create slack channel | NW | CA_San Mateo_66 21st Ave | San Mateo security improvements |  | 03/27 |  |  | We have a couple of security cameras out of order, also a request to install a few new cameras in order to improve the security past issues at the facility
P2 | Project Execution | 3/31 - Pending insulation. Expected to be completed on 4/4 | SW | AZ_Tempe_1900 E 5th St | Water heater audit | 286802209 286802223 286802235 286802243 286802248 | - | 2024-08-20 | 2024-12-31 | Water heater audit | Link | Weather Partners | 3835 | N/A | N/A | Facility Improvement | 10 years | 2025-01-30 | 511 | 3835 | PRJ.0027.07 | 3835 | 2025-02-17 | 2025-02-17 | 2025-02-24 |  | 3835
P2 | Project Execution | 3/31 - Pending insulation. Expected to be completed on 4/4 | SW | AZ_Phoenix_720 W Highland Ave | Water heater audit | 286802258 286802297 286802303 | - | 2024-08-20 | 2024-12-31 | Water heater audit | Link | Weather Partners | 5480 | N/A | N/A | Facility Improvement | 5 years | 2025-01-30 | 512 | 5480 | PRJ.0315.09 | 5480 | 2025-02-19 | 2025-02-19 | 2025-02-24 |  | 5480
P2 | Project Creation | 4/1 - To be completed in-house, expected for May | SW | CA_Van Nuys_14435 Victory Blvd | Cowl installation | 288997915 | - | 2024-09-09 | 2025-05-01 | Installation of a cowl on the DX Condenser to prevent the CU from damping hot air into the MAU | Check WO | FTM | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P2 | Project Creation | 1/20/2025: Pride missing some info from Chris | SW | CA_Culver City_5668 Selmaraine Dr | Water heater audit | 273028461 273028318 273028187 | - | 2024-03-26 | 2024-12-31 | Water heater audit | Link | Pride Construction | 1600 | N/A | N/A
P2 | Project Execution | Pending install of water heater circulation pump | SW | CA_Long Beach_1388 Daisy Ave | Water heater audit | 273026182 273025861 | - | 2024-03-26 | 2024-12-31 | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD
P2 | Project Execution | 4/1 - Started / In execution. Expected completition date 4/1 | SW | CA_Van Nuys_14435 Victory Blvd | Parking lot Re-stripping | N/A | - | 2025-03-31 | 2025-04-01 | The parking lot at Van Nuys is experiencing significant sinking, particularly around the grease interceptors. There are noticeable dips in the asphalt, leading to water pooling throughout the lot. After it rains, the entire area floods, causing operational issues and discomfort for businesses, including Starbucks. The standing water poses a safety concern for both vehicles and pedestrians, making immediate repairs necessary. | Link | FTM | 4800 | 48400 | N/A | Facility Improvement | 2 years | 2025-03-04 | 552 | 4800 | PRJ.0577.05 | 4800 | 2025-03-31 | 2025-03-31 | 4/12025 |  | 4800
P2 | Project Execution | 4/1 - Flue vents sealed, Joel to visit on 4/1 to install draft fans inside the ventos to exhaust the gas | SW | CA_Los Angeles_1411 W Sunset Blvd | Flue vent | 296559797 | - | 2025-02-19 | TBD | MAU-04 and MAU-05 not heating as there's a strong gas smell when turned on | N/A | FTM / Eng | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 |  | N/A
P3 | Project Development | 4/1 - To be completed in-house, date TBD | SW | CA_Anaheim_1560 S Lewis St | Hallway protection project | N/A | - | 2024-11-09 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | Check WO | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P3 | Project Creation | 4/1/2025: quoting installation of the exterior ladder to access the roof | SW | NV_Las Vegas_333 W St Louis Ave | Roof access Ladder | N/A | - | 2024-12-09 | TBD - 2025 | Need to install a new ladder to access the roof | Link Link: N/A; Pride Construction FTM: TBD; N/A N/A: Facility Improvement; N/A N/A: 10 years
P3 | Project Development | 4/1 - Not on scheduled yet, to be completed in-house | SW | CA_Los Angeles_1411 W Sunset Blvd | Exterior refurb | 302058862 | - | 2025-01-22 | TBD / Wants | Paint the exterior of the facility | N/A | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A
P3 | Project Development | 4/1 - Not on scheduled yet, to be completed in-house | SW | CA_Culver City_5668 Selmaraine Dr | Exterior refurb | N/A | - | 2025-02-17 | TBD / Wants | Paint the exterior of the facility | N/A | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A
P3 | Project Development | 4/1 - Pending quote from vendor and working on tech scheduling in parallel. Vendor completed the assessment and will send the quote this week | SW | CA_San Diego_2707 Boston Ave | Wall bumpers | N/A | - | 2025-04-15 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | N/A | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P3 | Project Development | 4/1 - To be completed in-house | SW | CA_Long Beach_1388 Daisy Ave | Hallway protection project | N/A | - | 2024-11-09 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | N/A | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P3 | Project Development | 4/1 - To be completed in-house | SW | CA_Culver City_5668 Selmaraine Dr | Hallway protection project | N/A | - | 2024-11-09 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | N/A | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A

## Import (hidden)
P0 | Completed! |  | NW | OR_Portland_1135 SE Grand Ave | Kitchen Split & Sinks Install | 294506155, 294595468 | 2024-08-30 | 2024-09-29 | 2024-07-11 | To perfom the division, 65 sqft of drywall needs to be installed. Tech will also install two new outlets, one on each side of the wall, and put the plastic sheet for kitchens use on top of the wall. This is a 6ftx14ft area. Tech will also connect the new compartment sink. The installation will take 18 hours to be completed. |  | N/A | 2040 | 4500 | 5000 | Facility Improvement | 10 Years | 8/21/2024 | 351 | $ 3,856.76 | PRJ.0184.03 | $ 3,856.79 | 8/28/2024 | 2024-04-09 | 8/30/2024 | 2024-11-11 | $ 3,856.79
P0 | Completed! |  | NW | WA_Seattle_1601 Dexter Ave N | Dexter Roof Fence | 279479275 | 2024-06-11 | 2024-07-11 | 11/22 | Techs will first clean the work area thoroughly, then drill holes and supply , install the metal posts and secure them to the ground, run new chain link fence around the posts, connect and weld them all together. Techs will then supply and install barbed wire arms on top, having razor wire wrapped around it. Techs will include a 4' x 3' man gate at the NW corner with lockable fork latch, including a top and bottom rail for support. Techs will then clean the working area and test repairs. |  | N/A | N/A | 6636 | N/A | Facility Improvement | 15 years | 2024-09-09 | 376 | $ 8,378.00 | PRJ.0557.03 | $ 6,636.00 | 45483 | TBD | 2024-11-10 | 11/22 | $ 6,636.00
Cancelled | Project Development | 11/19 - Getting new quotes for the services. 01/07 - Pending deck completion from OPS | NW | UT_Salt Lake City_23 N 900 W | SLC Entrace Improvements | 288722445 288722052 | 09/15 | On Hold |  | Entrace upgrade - Aesthetical 1 - Upgrade the landscaping 2 - Exchange door (improve visibility) 3 - Paint the neighbours wall 4 - Remove the tree 5 - remove archway and fence |  | N/A | Door quote | Pending | Pending | Facility Improvement
P0 | Completed! | 12/03 - Pending Invoice on SC | NW | CA_San Francisco_90 Charter Oak Ave | WIC Condensate Pans | 292394390 | 2024-10-10 | 2024-11-09 | 2024-05-11 | Furnish and install (3) pans and install under the condensing units and run PVC to a drain. This will prevent recurring costs of sealing the roof of the WIC and improve the experience of our clients. This will also prevent trip/fall hazard. |  | Link | 3300 | N/A | N/A | Facility Improvement | 10 years | 2024-11-10 | 432 | $ 3,300.00 | PRJ.0088.04 | $ 3,300.00 | 10/16/2024 | 2024-11-06 | 10/18/2024 | 2024-11-06 | $ 3,300.00
P0 | Completed! |  | NW | CA_Sunnyvale_1026 W Evelyn Ave | Sunnyvale Water Heaters Improvements | 286320555 | 2024-08-15 | 2024-08-18 | 2024-08-11 | Remove master mixing valve; Correct Heaters Discharge |  | N/A | 3100 | N/A | N/A | Facility Improvement | 15 years | 10/23/2024 | 446 | $ 3,100.00 | PRJ. | 3100 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 3100
P0 | Completed! | 10/31 - Darin is taking the plywood to SoMa to complete all the parts that are required for the designs application. 11/19 - Darin will be at Soma on Friday to replace the lights. Door installation is being studied by Paul. 12/03 - We had to include the lights in the SOW, the platform took more than expected. 12/10 - Still missing some details. Lights completed yesterday. Will be back on friday to complete ongoing 01/09 - Missing signage and details 01/21 - Pending confirmation 01/23 - Confirmed, completed | NW | CA_San Francisco_475 6th St | SoMa Lobby Refresh | Multiple WOs | 2024-10-24 | 2024-11-23 | 01/14 | The project includes, securing exposed mechanical equipment, fresh coat of pain + design & signage elements, an upgraded hand off window, and closing the gap around the cubbies. It also includes lighting, the space is dimly lit in the morning and evening leading to safety concerns. Project has been reviewed by ENT stakeholders. |  | Link | $ 10,286.00 | 15146 | N/A | Facility Improvement | 7 years | 09/20/2024 | 398 | $ 10,286.00 | PRJ.0008.03 | $ 10,286.00 | 9/30/2024 | 2024-10-24 | 10/18/2024 | 01/21 | $ 10,286.00
P0 | Completed! | 11/12 - Scheduled for 11/21 11/19 - Platforms installed | NW | CO_Aurora_14200 E Alameda Ave | Alameda MAU Platforms | 293738013 | 2024-10-22 | 2024-11-21 | 11/19 | No access to the MAUs 2, 3 and 4 |  | Deck | 1250 | 5500 | 6400 | Facility Improvement | 20 | 2024-11-05 | 463 | 3300 | PRJ.0310.06 | 3300 | 11/18 | 11/21 | 11/21 | 11/19 | 3300
P0 | Completed! | 11/19 - Work completed | NW | CA_San Jose_949 Ruff Dr | Ruff Dr Side Door Replacement | Multiple WOs | 2024-10-29 | 2024-11-28 | 11/19 | Side door replacement |  | N/A | 4985.28 | 8000 | 8000 | Facility Improvement | 10 years | 2024-06-11 | 464 | 5000 | PRJ.0241.07 | 5000 | 11/13 | 11/15 | 11/15 | 11/15 | 5000
On Hold | Project Execution | 12/10 - We proposed a meeting with Josh to pick solution for basement fan 01/07 - KEF Z1 pulley should be reinstalled. Mau 01 and 03 are mislabelled on BMS, ask German to help us with. 01/23 - Rescheduling Bayardo to reinstall the sheev, need to also install a pressure regulator in the gas line for the MAU of 2nd floor, pending quote. 01/30 - Ask Raphael to do a 2nd round of audit. 02/06 - Pending OPS Report | NW | CA_San Francisco_1200 Market St | Market Street HVAC Issues | Pending | 2024-10-22 | 2024-11-21 | 01/30 | HVAC Issues - Basement Temperature |  | N/A | Pending | Pending | Pending | Facility Improvement | 5 | NA | NA | 4000 | NA | NA | 10/22/2024 | 10/22/2024 | 01/30/2025 |  | NA
P0 | Completed! | 12/10 - Darin shared that there is a beam right above the lockers, this might be harder than expected 01/07 - Execution in Progress 01/09 - Pending aesthetical details 01/20 - Pending finishing | NW | CA_San Francisco_90 Charter Oak Ave | Charter Oak Lockers Install | Pending | 2024-12-10 | 01/15 | 2025-07-01 | Install new lockers, create a platform for the lockers, install new outlet and data port, and new mounts for the tablet. |  | N/A | NA | NA | NA | Facility Improvement | NA | NA | NA | NA | NA | NA | 2025-06-01 | 2025-06-01 | 2025-10-01 | 2025-07-01 | NA
P0 | Completed! | 10/07 - Waiting on Dickerson's proposal / Will Also send a WO to ICM 11/19 - Dickerson didn't deliver a proposal, waiting for ICM quote. 12/03 - Buy check valves and execute work with Chris FTM 12/10 - Chris ftm is on site checking execution details 01/07 - Execution ongoing 01/23 - New valves on site, scheduling in progress | NW | CO_Aurora_14200 E Alameda Ave | Check Valves installation | 274326420 295373288 | 2024-04-08 | On Hold | 01/28 | Check Valves installation |  | N/A | FTM | Universal Pros | ICM | Facility Improvement | 10 years | NA | NA | 1500 | NA | NA | 2025-06-01 | 2025-06-01 | 2025-08-01 | 01/28 | NA
On Hold | Project Development | 11/7 - Need to get 2nd and 3rd proposal. SOS's was to high 11/19 - Bayardo and RSC for quotes. | NW | CA_Redwood City_426 MacArthur Ave | Redwood City WH Improvements | 286993058 | 08/26 | On Hold |  | Contractor to bypass and remove the existing Leonard master mixing valve located at the water heaters. Extend the existing mixing valve HW inlet piping to connect to its HW outlet piping and remove the valve for a fully functional non-tempered HW supply to the building. Cap off and remove the existing CW branch line serving the mixing valve. Contractor to install (1) Zurn WXTP-50V floor mounted thermal expansion tank w/ SOV, connected downstream of the CW check valve in accordance with manufacturer's requirements. Contractor to install new time clock, set to turn ON one hour before the first Kitchen opens and OFF when the last Kitchen closes. Contractor to provide insulation for all bare exposed hot water and hot water return piping in the water heater room. |  | N/A | 8834 | Pending | Pending | Facility Improvement
P1 | Completed! | 12/03 - Bumpers install in progress, need at least 2 more full days, but it has been very hard to get that time available since we stopped using all the other vendors we had. 12/10 - Wednesday and Thursday we will have 2 full days with techs on site working on this 01/09 - Completion should be today 01/14 - Completion re-scheduled 01/21 - full day pending with 2 techs 01/22 - Completed | NW | CA_San Jose_949 Ruff Dr | Ruff Dr-Hallways Refresh | 298208087 | 2024-01-10 | 2024-02-09 | 01/23 | Hallways Refresh |  | N/A | N/A | N/A | N/A | Facility Improvement | 3 years | NA | NA | 3000 | NA | NA | 10/30 | 10/30 | 11/30 | 01/23 | NA
P1 | Completed! | 11/19 - Bayardo and RSC for quotes. 12/10 - Bayardo is looking for a mega press. Get 2 new plumbers on site to quote it. 01/09 - Evaluate quote from RSC and study In-house execution with more detail. 01/30 - Request sent for Mytrn. 02/06 - Darin is taking over the project once again., we need to align dates/costs/parts and schedule them. | NW | CA_San Mateo_66 21st Ave | San Mateo WH Improvents | 286171017 | 2024-08-13 | 2024-09-12 | 01/15 | The SOV downstream of the HW circulation pump is currently shut off, possibly stuck. I could not get to it as it is mounted in a hard to access location high up on the wall behind and above the water heaters. The SOV needs to be opened up. Unclear why this valve was closed. Check the HW circulation pump to see if it is operational. It does not have a time clock and is plugged into a receptacle. If it is turned on with no time clock or aquastat to control operation, it will have been running constantly with the downstream valve closed, which would cause it to cavitate and fail. If the circulation pump is non-operational, it needs to be replaced with a new one, and provided with a time clock set to turn it ON one hour before the first Kitchen opens, and OFF when the last Kitchen closes. A check valve needs to be installed on the HW circulation line upstream of where it ties into the CW line. The master mixing valve should be adjusted to its hottest possible setting. |  | N/A | FTM | Pending | Pending | Facility Improvement | 10 | NA | NA | NA | NA | NA | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | NA
P1 | Completed! | 11/19 - Push PMS and ask GSM for a quote 12/10 - Pending payments for PMS. 01/09 - Still on hold for payments, approved on 01/03. | NW | CA_Sacramento_1501 N C St | Sac WICCU07 Controller replacement | 302521343 | 2024-10-01 | 2024-10-31 | 02/15 | Get a quote from PMS for the replacement of the controller of the WICCU07 |  | N/A | 1500 | Pending | Pending | Facility Improvement | NA | NA | NA | 1500 | NA | NA | 01/29 | 01/29 | 01/29 | 01/29 | NA
P1 | Completed! | Darin will provide us a proposal 11/19 - Darin will inspect today 11/21 - Darin can do it on his next visit - schedule very early | NW | CA_Oakland_2353 E 12th St | Jingletown Gas Missing Dirt Leg | 290626081 | 2024-09-08 | 2024-10-08 | 12/17 | DEFICIENCY: WATER HEATERS MISSING DIRT LEG AT GAS CONNECTION. MITIGATION: INSTALL DIRT LEG AS REQUIRED PER CODE. |  | N/A | Pending | Pending | Pending | Facility Improvement | 20 years | NA | NA | NA | NA | NA | 12/17 | 12/17 | 12/17 | 12/17 | NA
On Hold | Project Development | Waiting on tech's availability | NW | CA_Oakland_2353 E 12th St | Jingletown-Hallways Refresh | Pending | 2024-10-01 | On hold |  | Hallways Refresh |  | N/A | Pending | Pending | Pending | Facility Improvement
On Hold | Project Creation | 02/06 - Pending techs availbility. deprioritized for now | NW | OR_Portland_1135 SE Grand Ave | Portland Ansul Corrections | Pending | Still under review | On hold |  | Correct the installation of the Ansul systems, if it is really necessary. Johnson indicates that all the bottles that are mounted on the wall should have hard piped lines instead of rubber hoses.
Cancelled | Project Development | 11/27 - Quoting with united electric 12/04 - Proposal arrived 12/10 - Pending justification for the project from OPS | NW | ID_Boise_1744 W Main St | Boise - External lights | 295800335 | 2024-11-13 | On hold |  | The purpose of this project is to install four 5-foot LED light bars along the front exterior of the business to improve nighttime visibility of brand advertising displayed on vinyl-covered windows. These vinyl graphics are clearly visible during the day, but at night, the contrast caused by stronger interior lighting diminishes the external visibility of the branding. The installation of high-lumen LED light bars will ensure the vinyl display maintains its intended visibility and impact during all hours, aligning with brand presentation goals. Specifications and Considerations: • The light bars should provide a lumen output equal to or exceeding that of the interior lighting, creating balanced illumination between the interior and exterior. • Placement should be optimized for uniform lighting coverage across the entire front, ensuring consistent brightness and no shadowed areas. • Considerations should be made for secure, weather-resistant mounting, as well as any necessary electrical wiring or fixtures required for efficient, long-term use. This lighting enhancement is expected to improve brand recognition and visibility, contributing to an inviting and professional appearance for passersby and potential customers after dark. |  | N/A | 2377 | Pending | Pending
Cancelled | Project Creation | 12/10 - JC already done one part. Negotiate with DEV for payment. Align with DEV+OPS for the rest of the corrections with Miguel de Tekas 1) Get list of tanks that are missing 2) Get the tanks from dev (Kaitlyn) 3) Include it in the process onboarding | NW |  | Seattle Ansul Corrections | Pending |  |  |  | Complete the installation of the Ansul systems in the kitchens that are operating.
P0 | Completed! | 12/10 - Meridian OK 01/09 - Pending Scheduling 01/23 - Scheduled with merdian for Monday 01/27 01/30 - Vent caps installed, pending tank replaccement | NW | CO_Denver_810 N Vallejo St | Vallejo Ansul Corrections | 297763185 297763305 | 2024-11-07 | 2024-12-07 | 01/27 | Mutiple corrections in Ansul systems |  | N/A | 1700 | 1300 | NA | Facility Improvement | 2 years | NA | NA | 3000 | NA | NA | 01/25 | 01/25 | 01/25 | 01/25 | 3000
P1 | Completed! | 12/5 - Dickerson scheduled to install 12/10 - DIckerson is on site 01/07 - Completed | NW | CO_Aurora_14200 E Alameda Ave | Aurora - Replace VFDs | 295701978 | 2024-10-15 | 2024-11-14 | 2025-12-12 | Install new VFD's in the MAUs |  | N/A | 1360 | NA | NA | Repair | 5 years | NA | NA | 3054 | PRJ.0310.07 | 3800 | 2024-10-12 | 2024-12-12 | 2025-10-12 | 2024-12-12 | 3054
On Hold | Completed! | 11/19 - Get 2 more quotes 11/27 - Quotes arrived, pending cc liberation 12/13 - Vendor backed up, tried a second one, he only accepted cash or check. We will need to put more energy into this next quarter | NW | CA_San Jose_949 Ruff Dr | Ruff Dr Paking Lot | Pending | 2024-09-12 | 2024-10-12 | 12/13 | Parking Lot - potholes repairs |  | N/A | 3432 | 2000 | 2800 | Facility Improvement | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Cancelled | Project Development | 11/19 - Put a hard limit for the project 12/15. 12/03 - Asked Raphael to support us with color decision. Sergio will get a quote with a vendor for comparison. | NW | CA_Oakland_2353 E 12th St | JT Graffiti Removal | 281666592 | 2024-07-27 | 2024-08-26 | 01/20 | Repaint of the graffiti wall - Cover gang sign graffities |  | N/A | Pending | Pending | Pending | Facility Improvement
P0 | Project Development | 04/01 - Ricardo is detailing SOW - ETA 04/04 We need to find two roofing vendors 01/09 - Reach out to Kaitlyn to understand if she was able to get a new quote 01/28 - Channel created for the roof coating, Chris will help us build a quote using in-house techs 02/06 - Detail parts of the job, and get quotes for each part | NW | CA_Hayward_1025 A St | Roof Coating | Pending | 2024-11-07 | 2024-12-07 | 2025-04-30 | We need to cover the leaks at the roof. This were mapped out with the construction team. Now we need to get different proposals |  | N/A | 54075 | 18000 | Analyzing FTM | Facility Improvement | 20
P0 | Project Execution | 04/01 - In-house, Darin+1, parts on site; ETA 04/04; Proposal sent- ready for approval 03/20 - Pending approval 03/25 - Vendor Proposal not approved, services scheduled in-house | NW | CA_Sacramento_1501 N C St | Sacramento new exterior lights | 298427608 | 2025-01-30 | 2025-03-01 | 2025-04-04 | WOs in the past: 268647400, 294125444. We have reinstalled the current lights multiple times. We would like to replace it for another model. |  | N/A | 1230 | NA | NA | Repair | 5 | NA | NA | 1800 | NA | NA | 03/27 |  | 03/27
Cancelled | Project Development | 12/03 - Pending on validation of SOW from Reza 12/10 - Probably not going to be a large project, no card reader will be needed, they need to adjust sensors and operation. | NW | CA_San Jose_96 E Santa Clara St | Clara Open Path | Pending | 2024-10-01 | 2024-10-31 |  | Install readers for the doors of 86 E Santa Clara and tell OPS that they can adjust schedules |  | N/A | Pending | Pending | Pending | Facility Improvement
P0 | Project Execution | 04/01- Wiring is ok, most of the project is completed; ETA 04/04 03/24 - Buying parts | NW | CA_San Francisco_1200 Market St | Market Street security improvement | 303478381 | 2025-02-15 | 2025-03-17 | 2025-04-04 | Install new cables to upgrade openpath comms |  | N/A | 3133 | N/A | N/A | Facility Improvement | 5 years | 2025-03-20 | 558 | 3133 | PRJ.0570.07 | 3133 | 03/26 |  | 03/28 |  | 3933
P1 | Project Execution | 04/01 - Team is replacing FRP panels; missing another execution round. ETA 04/08 12/03 - Allign with Darin, get parts and include in scheduling. 01/30 - Count how many FRP boards are needed 02/06 - Buy parts and schedule 03/20 - Schedule full team and add corrections of the lobby. Get lobby pictures and share in the channel to close the channel. | NW | CA_San Francisco_475 6th St | Soma-Hallways Refresh | 302652851 | 2024-12-02 | 2025-01-01 | 2025-04-08 | Clean FRP Better attach the FRP boards to the walls Install bumper guards Repatch the wholes of the shelves that were removed (and replace some panels) |  | N/A | 1200 | N/A | N/A | Facility Improvement | 3 years | NA | NA | 1200 | NA | NA | 02/17 |  | 02/30 |  | NA
P1 | Project Execution | 04/01 - Jay will tackle this when he is back, probably a whole week. ETA 04/15 Cove Base application in progress We need to buy the bumpers 01/09 - Get measurements for the bumpers to bauy and install them 01/23 - Buy cove base and bumper guards 02/06 - Cove base arrived - execution scheduled over the next few days. Buy the bumper guards 03/20 - Schedule north techs 2 days next week | NW | CA_Oakland_5333 Adeline St | Adeline-Hallways Refresh | 302650180 302652158 | 2024-10-01 | 2024-10-31 | 2025-04-15 | Hallways Refresh |  | N/A | FTM | NA | NA | Facility Improvement | 3 | NA | NA | 3000
P1 | Project Creation | 04/01 - Update channel with expected days/scope/details 02/06 - Paint the lobby for the project execution - coordinate with Reza for the execution 03/20 - In theory this is only painting | NW | CA_San Jose_949 Ruff Dr | Ruff Drive Lobby Refresh | Pending | 2025-02-06 | 2025-03-08 |  | Paint the wall and improve the trimm of the lockers
P1 | Project Creation | 04/01 - Deatil scope with Casey | NW | OR_Portland_1135 SE Grand Ave | Portland Trash room heating |  | 03/27
P1 | Project Creation |  | NW | CA_San Francisco_90 Charter Oak Ave | New side door for Charter Oak
P2 | Project Execution | 04/01 - Revise SOW to validate if we can create a Capex Project for it; 11/19 - Get quotes 12/10 - Captain plumbing 01/09 - Invite Captain Plumbing to meeting 01/14- made contact with Tony Moya (captain plumbing), setting meeting for next week 01/23 - Ricardo to get other quotes 02/06 - 3 quotes completed, ask for approval 03/20 - Pending voided check | NW | UT_Salt Lake City_23 N 900 W | SLC BFP rebuild | Pending | 2024-07-10 | 2024-08-09 | 2024-12-12 | Rebuild the backflow prevention device |  | N/A | 5000 | 1960 | 2388 | Facility Improvement | 10 years | NA | NA | 1960 | NA | NA | 2025-01-04 |  | 2025-10-04 |  | 1960
P2 | Project Development | 04/01 - Pending quote Darin will provide us a proposal 11/19 - Darin declined 12/03 - Dispatched to Bayardo. Scheduled for 12/05 01/09 - Reach out to Bayardo for FUP 02/06- Look for new vendors | NW | CA_San Francisco_90 Charter Oak Ave | Charter Gas Missing Dirt Leg | 302592544 | 2024-09-08 | 2024-10-08 | 12/20 | DEFICIENCY: WATER HEATERS MISSING DIRT LEG AT GAS CONNECTION. MITIGATION: INSTALL DIRT LEG AS REQUIRED PER CODE. |  | N/A | 4032.12 | 4275 | Pending | Facility Improvement
P2 | Project Development | 04/04 - Pending quote from new vendor; 01/28 - Reach out for new quotes: Taylor electric, Fix & Finish 02/05- Taylos electric charges $95 just for the visit 02/06 - Fix&finish doesnt provide this service, only basic electrical jobs 02/06 - Contacted Restaurant Service Solutions /Victor Mendoza, to get an estimate, request sent 03/20 - Still trying to get a new quote for the labor | NW | UT_Salt Lake City_23 N 900 W | SLC Security Breakers | 297573193 | 2024-12-03 | 2025-01-02 | 02/28 | Install the surge protection devices in the main panel |  | Link | 5191.16 | SURGE ARRESTOR DATA SHEET | Taylor electric, trying to get an estimate without visit cost
P2 | Project Creation | 04/01 - Buy parts on 04/08 - and execute as soon as we complete Adeline; 03/20 - Pending bumper guards | NW | CA_San Francisco_90 Charter Oak Ave | Charter Oak Bumper Guards | Pending | 2025-06-02 | 2025-07-02 |  | REAL MEASUREMENT IS 210ft |  |  | FTM
P2 | Project Creation | 04/01 - Quote awning with in-house install or get a broader SOW for Capex; 03/20 - Define project scope | NW | CA_San Jose_949 Ruff Dr | Ruff drive rain protection for catering |  | 2025-03-19 | 2025-04-18 |  |  |  |  | 2306 | 2311
P2 | Project Creation | 04/01 - Get quote from Darin 03/20 - Buy parts | NW | CA_San Mateo_66 21st Ave | San Mateo WH Improvents 2nd phase |  | 2025-03-20 | 2025-04-19 |  | The existing thermal expansion tank is undersized and needs to be replaced with a new Zurn WXTP-50V floor mounted model. Each of the (2) water heater condensate drain lines are missing acid neutralization kits. Provide new Acid Neutralization Kits; Mfr: Neutra-Safe or equal, with inlet and outlet sizes to match existing condensate drain pipe.
P2 | Project Creation | 04/01 - Get detailed SOW with OPS and quote parts+instal 03/27 Create slack channel | NW | CA_San Mateo_66 21st Ave | San Mateo security improvements |  | 03/27 |  |  | We have a couple of security cameras out of order, also a request to install a few new cameras in order to improve the security past issues at the facility
P2 | Project Execution | 3/31 - Pending insulation. Expected to be completed on 4/4 | SW | AZ_Tempe_1900 E 5th St | Water heater audit | 286802209 286802223 286802235 286802243 286802248 | - | 2024-08-20 | 2024-12-31 | Water heater audit | Link | Weather Partners | 3835 | N/A | N/A | Facility Improvement | 10 years | 2025-01-30 | 511 | 3835 | PRJ.0027.07 | 3835 | 2025-02-17 | 2025-02-17 | 2025-02-24 |  | 3835
P2 | Project Execution | 3/31 - Pending insulation. Expected to be completed on 4/4 | SW | AZ_Phoenix_720 W Highland Ave | Water heater audit | 286802258 286802297 286802303 | - | 2024-08-20 | 2024-12-31 | Water heater audit | Link | Weather Partners | 5480 | N/A | N/A | Facility Improvement | 5 years | 2025-01-30 | 512 | 5480 | PRJ.0315.09 | 5480 | 2025-02-19 | 2025-02-19 | 2025-02-24 |  | 5480
P2 | Completed! | 2/17: vendor will re-deliver the door this week | SW | CA_Anaheim_1560 S Lewis St | Wingstop's sliding glass door | 294121761 | - | 2024-10-25 | 2025-01-31 | Install of sliding glass door. Wingstop requested it be installed prior to their opening at 10AM | Check WO | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-02-25 | N/A
P1 | Completed! | Completed | SW | CA_Lawndale_16711 Hawthorne Blvd | Picnic | 293847983 | - | 2024-10-23 | N/A | Picnic re-branding | Check WO | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P2 | Completed! | Completed | SW | CA_San Diego_6334 El Cajon Blvd | FOG tanks outlet | 292392271 | - | 2024-10-10 | N/A | Change the receptacle on the outlet at the rear of the building to accommodate for the new FOG tank. | Check WO | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P1 | Project Development | 4/1 - Cesar scheduled for 4/24 | SW | CA_Culver City_5668 Selmaraine Dr | Retrofit all MAUs | N/A | - | 2024-09-25 | 2025-04-01 | Retrofit all MAUs with new pumps and float valves | Check WO | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A
P2 | Completed! | Completed | SW | CA_Costa Mesa_1750 Newport Blvd | Enclosure | 290233257 | - | 2024-09-18 | N/A | Completed | Check WO | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P3 | Project Development | 4/1 - To be completed in-house, date TBD | SW | CA_Anaheim_1560 S Lewis St | Hallway protection project | N/A | - | 2024-11-09 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | Check WO | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P2 | Project Creation | 4/1 - To be completed in-house, expected for May | SW | CA_Van Nuys_14435 Victory Blvd | Cowl installation | 288997915 | - | 2024-09-09 | 2025-05-01 | Installation of a cowl on the DX Condenser to prevent the CU from damping hot air into the MAU | Check WO | FTM | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P2 | Completed! | To be completed in-house | SW | CA_Van Nuys_14435 Victory Blvd | Water heater audit | 286998634 286998634 | - | 2024-08-22 | TBD | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2025-01-14 | N/A
P0 | Completed! | Completed | SW | CA_Los Angeles_615 N Western Ave | Grease trap covers replacement | 286356642 | - | 2024-08-15 | 2024-12-31 | Grease trap covers are damaged and oxidized. Observed some cracks which can cause the trap to break and hurt someone. | Check WO | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | N/A
P2 | Completed! | To be completed in-house | SW | CA_San Diego_2707 Boston Ave | Water heater audit | 283834938 | - | 2024-07-19 | 2024-12-31 | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2025-01-13 | N/A
P2 | Completed! | To be completed in-house | SW | CA_Los Angeles_1842 W Washington Blvd | Hallway protection project | 278738602 | - | 2024-05-28 | 2024-12-31 | Install wall guards 30" up the wall; install 6" black cove base on the bottom of the wall. | Check WO | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2024-12-24 | N/A
P1 | Project Creation | Need to run plumbing line from main line to the water softener (to be completed by FTM), after this, final install to be completed by Culligan | SW | CA_San Diego_6334 El Cajon Blvd | Water heater audit | N/A | - | 2024-03-26 | TBD / June 2025 | Water softener is not working | Link | FTM / Culligan | N/A | N/A | N/A | Facility Improvement
P2 | Project Creation | 1/20/2025: Pride missing some info from Chris | SW | CA_Culver City_5668 Selmaraine Dr | Water heater audit | 273028461 273028318 273028187 | - | 2024-03-26 | 2024-12-31 | Water heater audit | Link | Pride Construction | 1600 | N/A | N/A
P2 | Project Execution | Pending install of water heater circulation pump | SW | CA_Long Beach_1388 Daisy Ave | Water heater audit | 273026182 273025861 | - | 2024-03-26 | 2024-12-31 | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD
P2 | Completed! | To be completed in-house | SW | CA_Anaheim_1560 S Lewis St | Water heater audit | 273024513 273024063 | - | 2024-03-26 | 2024-12-31 | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2025-02-04 | N/A
P2 | Completed! | To be completed in-house | SW | CA_Los Angeles_1842 W Washington Blvd | Water heater audit | 273022840 273022448 273022064 | - | 2024-03-26 | 2024-12-31 | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 2025-01-05 | N/A
P2 | Completed! | Bypass to me completed on March 10 | SW | CA_Los Angeles_615 N Western Ave | Water heater audit | 273021510 273021314 273020709 | - | 2024-03-26 | 2025-03-10 | Water heater audit | Link | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-04 | N/A
P3 | Project Creation | 4/1/2025: quoting installation of the exterior ladder to access the roof | SW | NV_Las Vegas_333 W St Louis Ave | Roof access Ladder | N/A | - | 2024-12-09 | TBD - 2025 | Need to install a new ladder to access the roof | Link Link: N/A; Pride Construction FTM: TBD; N/A N/A: Facility Improvement; N/A N/A: 10 years
P2 | Project Execution | 4/1 - Started / In execution. Expected completition date 4/1 | SW | CA_Van Nuys_14435 Victory Blvd | Parking lot Re-stripping | N/A | - | 2025-03-31 | 2025-04-01 | The parking lot at Van Nuys is experiencing significant sinking, particularly around the grease interceptors. There are noticeable dips in the asphalt, leading to water pooling throughout the lot. After it rains, the entire area floods, causing operational issues and discomfort for businesses, including Starbucks. The standing water poses a safety concern for both vehicles and pedestrians, making immediate repairs necessary. | Link | FTM | 4800 | 48400 | N/A | Facility Improvement | 2 years | 2025-03-04 | 552 | 4800 | PRJ.0577.05 | 4800 | 2025-03-31 | 2025-03-31 | 4/12025 |  | 4800
P1 | Project Creation | 4/1 - Project to be completed by construction | SW | CA_Santa Ana_2509 S Broadway | Water softener installation | N/A | - | TBD | TBD | Need to install water softener. Construction working on this | Link Link: N/A; Pride Construction FTM: N/A; 1600 N/A: N/A; N/A N/A: N/A; N/A N/A: N/A; N/A N/A: N/A
P1 | Completed! | Completed | SW | AZ_Tempe_1900 E 5th St | Openpath install | 300761580 | - | 2025-02-17 | 2025-02-21 | Openpath install | N/A | Downtown Locksmiths | 3012.32 | N/A | N/A | Facility Improvement | N/A | 2025-01-30 | 510 | 3012.32 | PRJ.0027.06 | 3012.32 | 2025-02-10 | 2025-02-17 | 2025-02-12 | 2025-02-18 | 3012.32
P0 | Completed! | Completed | SW | AZ_Tempe_1900 E 5th St | Tree removal | 303771742 | - | 2025-02-13 | 2025-02-13 | Need to remove tree | N/A | AME Lanscape | 2940 | N/A | N/A | Facility Improvement | N/A | 2025-02-06 | 520 | 2940 | PRJ.0027.09 | 2940 | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-14 | 2940
P0 | Completed! | Completed | SW | AZ_Tempe_1900 E 5th St | Planting | N/A | - | 2025-02-14 | 2025-02-14 | Need to plant trees according to inspection | N/A | Treeland Nurseries | 3605 | N/A | N/A | Facility Improvement | N/A | 2025-02-06 | 521 | 3605 | PRJ.0027.08 | 3605 | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 | 3605
P3 | Project Development | 4/1 - Not on scheduled yet, to be completed in-house | SW | CA_Los Angeles_1411 W Sunset Blvd | Exterior refurb | 302058862 | - | 2025-01-22 | TBD / Wants | Paint the exterior of the facility | N/A | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A
P3 | Project Development | 4/1 - Not on scheduled yet, to be completed in-house | SW | CA_Culver City_5668 Selmaraine Dr | Exterior refurb | N/A | - | 2025-02-17 | TBD / Wants | Paint the exterior of the facility | N/A | FTM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A
P3 | Project Development | 4/1 - Pending quote from vendor and working on tech scheduling in parallel. Vendor completed the assessment and will send the quote this week | SW | CA_San Diego_2707 Boston Ave | Wall bumpers | N/A | - | 2025-04-15 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | N/A | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P2 | Project Execution | 4/1 - Flue vents sealed, Joel to visit on 4/1 to install draft fans inside the ventos to exhaust the gas | SW | CA_Los Angeles_1411 W Sunset Blvd | Flue vent | 296559797 | - | 2025-02-19 | TBD | MAU-04 and MAU-05 not heating as there's a strong gas smell when turned on | N/A | FTM / Eng | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 |  | N/A
P0 | Project Execution | 4/1 - Scheduled for April 28th to April 30th | SW | CA_Long Beach_1388 Daisy Ave | MAU drains | N/A | - | 2025-04-28 | 2025-04-01 | Water draining from the MAUs go directly to the street | N/A | FTM | N/A | N/A | N/A | Repair | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-20 |  | N/A
P0 | Project Creation | 4/1: eng recommends to Apply sealing paint as a fix | SW | CA_San Diego_2707 Boston Ave | MAU-05 | 285292405 | - | 2024-08-04 | TBD - April 2025 | MAU-05 is currently leaking, drain pan needs to be replaced. Unit has to be dis-assembled to change the pan | Link Link: Check WO; Pride Construction FTM: FTM
P0 | Project Development | 4/1 - Parts on order (ETA 4/4), to be scheduled with Joel and Cesar for April 21st | SW | CA_Anaheim_1560 S Lewis St | MAU-02 blower wheel | N/A | - | 2024-09-01 | 2025-04-23 | MAU 2A: The blower wheel assembly has damaged bearings and a grooved shaft, requiring a full replacement. MAU 2D (Blower #4): The blower wheel assembly also has damaged bearings and a grooved shaft, necessitating a replacement | N/A | FTM / Eng | 7880.46 | N/A | N/A | Facility Improvement | 5 years | 2024-08-21 | 352 | 7880.46 | PRJ.0239.07 | 7880.46 | 2025-04-23 |  | 2025-04-25
P3 | Project Development | 4/1 - To be completed in-house | SW | CA_Long Beach_1388 Daisy Ave | Hallway protection project | N/A | - | 2024-11-09 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | N/A | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P3 | Project Development | 4/1 - To be completed in-house | SW | CA_Culver City_5668 Selmaraine Dr | Hallway protection project | N/A | - | 2024-11-09 | TBD | Hallway protection project: (1) remove bottom 6" of drywall and replace with 5/8" cement board (2) install 6" black cove base on the bottom of the wall. (3) Repaint facility walls white (4) install new corner guards that reach to cove base (5) install wall guards 30" centered up the wall | N/A | FTM | N/A | N/A | N/A | Facility Improvement | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A
P0 | Project Development | 4/1 - The temporary solution will last around 6 months, all the recommendations proposed by the vendor to be completed under project. Expected start date 4/3 | SW | AZ_Tempe_1900 E 5th St | Roof | 305138797 | - | 2025-03-07 | 2025-04-03 | Remove existing roof compromised by moisture and remove drip edge, Install new foam roofing and new drip edge metal. | Link | TBD | 8975 | 8700 | N/A | Facility Improvement | N/A | 2025-03-18 | 557 | 8975 | PRJ.0027.10 | 8975 | 2025-04-03 |  | 2025-04-09 |  | 8975
P0 | Project Development | 4/1 - Vendor's recommendations approved on 3/30. Expected start date 4/10 | SW | AZ_Phoenix_720 W Highland Ave | Roof | 306516223 | - | 2025-03-06 | 2025-04-15 | Remove damaged foam roofing and replace with SPF | Link | TBD | 2500 | 20000 | N/A | Facility Improvement | N/A | 2025-03-28 | 565 | 2500 |  | 2500 | 2025-04-16 |  | 2025-04-18 |  | 2500
P1 | Project Creation | 4/1 - Selected proposal sent for pre-approval | SW | AZ_Tempe_1900 E 5th St | Exterior lights | 305882961 | - | 2025-02-27 | 2025-04-23 | Install new lights in the parking lot | Link Link: N/A; Pride Construction FTM: JFK Electric; 1600 N/A: 6500; N/A N/A: 4189; N/A N/A: N/A; N/A N/A: Facility Improvement
P0 | Project Creation | 4/1 - Expense request sent | SW | AZ_Tempe_1900 E 5th St | Grease traps column | 305139552 | - | 2025-02-21 | 2025-04-28 | Replace the concrete columns of both grease traps | Link Link: N/A; Pride Construction FTM: 3D Pipelines; 1600 N/A: 6307.89; N/A N/A: 6450; N/A N/A: N/A; N/A N/A: Facility Improvement
P0 | Project Creation | 4/1 - First camera inspection didn't show any blockage. Second camera inspection scheduled for 4/2 with longer reach | SW | AZ_Tempe_1900 E 5th St | Parking lot drain | 307270329 | - | 2025-03-13 | 2025-04-15 | Drain inspection, camera re-inspection scheduled for 4/1 | Link Link: N/A; Pride Construction FTM: TBD
P0 | Project Creation | 4/1 - Waiting for quote from vendors, Joseph Kemp to send new Openpath Box | SW | AZ_Tempe_1900 E 5th St | Openpath install single door | N/A | - | 2025-03-26 | 2025-04-23 | Joseph Kemp to send additional Openpath box, vendors contacted to provide quote for install | Link Link: N/A; Pride Construction FTM: Downtown Locksmiths
P1 |  |  | SW | AZ_Tempe_1900 E 5th St | Double door delivery | N/A | - |  |  | Chris will go and evaluate with Jareth
P1 | Project Creation | 4/1 -Parts requested with procurement. Installation in-house | SW | CA_Lawndale_16711 Hawthorne Blvd | Water heater re-circ pump | N/A | - | 2025-03-24 | TBD | Need to replace the water heater recirculation pump | Link Link: N/A; Pride Construction FTM: FTM
P1 | Project Creation | 4/1 - Waiting on quote | SW | CA_Lawndale_16711 Hawthorne Blvd | Fire alarm panel | N/A | - | 2025-03-17 | 2025-04-20 | Need to replace panel due to water damage | Link Link: N/A; Pride Construction FTM: Pacific Signaling

## Floors Western
| Date | Hours | Scope of work | Closed areas
Day 1 | 2025-03-24 | 6am-2pm
Day 2 | 2025-03-25
Day 3 | 2025-03-26
Day 4 | 2025-03-27
Day 5 | 2025-03-28
Day 6 | 2025-03-31
Day 7 | 2025-04-01
Day 8 | 2025-04-02
Day 9 | 2025-04-03
Day 10 | 2025-04-04
Day 11 | 2025-04-07
Day 12 | 2025-04-08
Day 13 | 2025-04-09